## Cover
GACP Platform
Engineering Session — 2026-04-28
ระบบรับรองมาตรฐาน GACP สำหรับสมุนไพร · กระทรวงสาธารณสุข
Generated | 2026-04-28T14:36:00Z (post-deploy v3.4.2)
Source | git log + /var/log/gacp-deploys/ + /var/log/gacp-secret-rotations.log
Production droplet | 152.42.218.251 (ubantu-2p-webapp)
Production URL | https://gacpth.com
Sheet index
Sheet | Description
Cover | this sheet — generation metadata
PRs Merged | all 18 pull requests with branch, title, merge time, LOC delta, risk
Deploys | v3.3.0 baseline + v3.4.0/14.1/14.2 — image digests, DB snapshot, health
Secret Rotations | 5 entries from /var/log/gacp-secret-rotations.log
Audit Findings | 35 server hygiene checks (§12 audit) with severity + action taken
Decisions Pending | 3 go/no-go items waiting on operator
Counts (auto)
PRs merged
Production deploys today
Secret rotations (incl. rollback)
Audit findings checked
Decisions pending

## PRs Merged
PR# | Branch | Title | Merged at (UTC) | LOC delta | Risk
6 | fix/ci-yaml-cr-corruption | CR-byte fix in workflow YAML | earlier today | small | low
7 | fix/health-application-urgent-ux | 5 applicant UX fixes (plot/draft/multi-purpose/required-doc) | earlier today | medium | low
8 | fix/health-canonical-m1-docs | 3-form M1 ภท.09/10/11 dedup | earlier today | small | low
9 | fix/p0-bugs-from-audit-2026-04-28 | 8 P0 production bugs (cert template / pdf path / fee math / etc) | 13:30:51 | 170 | medium
10 | docs/system-cohesion-review | 5 domain audits + master synthesis plan | 13:32:02 | 1590 | none
11 | fix/migration-drift-comprehensive | 3 missing tables backfill (scope_of_works/audit_checklists/meeting_rooms) | 13:34:36 | 244 | medium
12 | feat/server-hygiene-phase-b-codeable | pg-backup cron + secret-rotation + GHCR cleanup + logrotate | 13:31:42 | 895 | low
13 | docs/erp-grade-review | ERP architectural review (Odoo benchmark) | 13:31:55 | 590 | none
14 | fix/deploy-scripts-executable-bit | 14 .sh files chmod +x via git index | 13:30:31 | 0 (mode-only) | low
15 | feat/seed-erp-fixtures | Farm/Plot/PlantSpecies + canonicalId FK | 13:31:48 | 350 | low
16 | feat/readiness-check-ci-mode | production-readiness-check skip-on-no-server | 13:30:45 | small | low
17 | fix/workflow-rejected-lab-state | REJECTED_LAB undefined-state hole closed | 13:31:02 | medium | low
18 | chore/repo-hygiene-phase-a | Phase A artifact cleanup | 13:31:32 | -690 | low
19 | fix/phase-amount-caller-canonical-semantics | preview.js + review-revision callers canonical | 13:31:15 | medium | medium
20 | fix/e2e-playwright-install | Playwright cache install path | 13:30:38 | small | low
21 | feat/ci-preventive-controls | lint ratchet + workflow paths + schema drift gate | 13:35:41 | 1200 | low
22 | fix/applicant-feedback-batch-2 | plot validation/draft resume/multi-purpose/req docs | 13:31:09 | 470 | medium
23 | fix/billing-followups-from-caller-audit | rename CONFIG + seed feeService + schema defaults + drift test | 13:31:22 | 380 | low

## Deploys
Tag | Deployed at (UTC) | Image digest | Highlights | DB snapshot | Health post
v3.3.0 | baseline (pre-session) | sha256:1079a7… | previous version (running before today's session began) | — | 200
v3.4.0 | 13:36 | sha256:2ae9a4… | Audit follow-up wave: 8 P0 + migration drift + REJECTED_LAB + repo hygiene Phase A + server hygiene Phase B | /var/backups/gacp/gacp-pre-deploy-20260428-135046.sql.gz | 200
v3.4.1 | 14:08 | sha256:0789b2… | Ministry phone correction: 0-2965-9000 → 0-2591-7007 (verified from dtam.moph.go.th footer) | /var/backups/gacp/gacp-pre-deploy-20260428-140848.sql.gz | 200
v3.4.2 | 14:36 | sha256:47604a… | User-feedback hot-fix: canonical phase status in payload + payment-page waiting banner + rotate-secret SMOKE_URL fix | /var/backups/gacp/gacp-pre-deploy-20260428-143644.sql.gz | 200

## Secret Rotations
Timestamp (UTC) | Action | Secret | Backup file | Note
2026-04-28T14:21:58Z | ROLLBACK | PAYMENT_WEBHOOK_SECRET | .env.production-20260428T142102Z.bak | Script bug — SMOKE_URL was http://127.0.0.1:8000/api/health (Express direct), but prod nginx is on :80. Smoke failed → auto-rollback. Script patched, rotation retried.
2026-04-28T14:38:30Z | ROTATED | PAYMENT_WEBHOOK_SECRET | .env.production-20260428T143819Z.bak | After SMOKE_URL fix. New 64-char base64url secret.
2026-04-28T14:38:46Z | ROTATED | QR_SIGNATURE_FALLBACK_SECRET | .env.production-20260428T143834Z.bak | Existing QR codes still verify (primary signing key unchanged).
2026-04-28T14:39:02Z | ROTATED | HEALTH_JWT_SECRET | .env.production-20260428T143850Z.bak | All currently-logged-in applicant users will need to log in again on next request.
2026-04-28T14:39:19Z | ROTATED | PROVIDER_JWT_SECRET | .env.production-20260428T143906Z.bak | Same logout effect for officer / reviewer / auditor / scheduler / accounts / admin tokens.

## Audit Findings
Category | Item | Status | Severity | Action taken
System | Uptime | OK | info | 18 days, load avg 0.73 — comfortable
System | Kernel | OK | info | 6.8.0-107-generic
Disk | / usage | OK | info | 50% (57G of 116G)
Disk | Inode usage | OK | info | 11%
Disk | /var/log size | OK | info | 1.1G — fine
Memory | Free memory | OK | info | 5.9G available of 7.8G
Network | Open ports | OK | info | 443/22/80 + 9000/9001/9090 internal
Network | ufw status | OK | info | active
Network | fail2ban | OK | info | active
TLS | gacpth.com cert | OK | info | expires 2026-06-13 (45 days remaining); certbot.timer scheduled 2026-04-29 05:00 UTC
Docker | Running containers | OK | info | 11 (0 unhealthy, 0 stopped)
Docker | Dangling images | fixed | low | 1 dangling — pruned (0 B reclaimed; was actually attached)
Docker | Dangling volumes | info | low | 5 listed — none truly orphaned, prune reclaimed 0 B
GACP | Backend image | OK | info | ghcr.io/jonmaxmore/gacp-backend:v3.4.2
GACP | Frontend image | OK | info | ghcr.io/jonmaxmore/gacp-frontend:v3.4.2
GACP | Backend health | OK | info | /api/health 200, https://gacpth.com 200
GACP | Database schema | OK | info | Up to date — 37 migrations applied
Backup | Daily pg_dump cron | fixed | low | INSTALLED /etc/cron.d/gacp-backup at 02:17 daily (was missing)
Backup | Logrotate config | fixed | low | INSTALLED /etc/logrotate.d/gacp-platform; needed `su root root` patch (was missing)
Backup | Latest DB backup | OK | info | v3.4.0/14.1/14.2 pre-deploy snapshots present in /var/backups/gacp/
SSH | Password authentication | fixed | high | WAS yes → fixed to no (verified 6 keys before flip)
SSH | Root login | OK | info | PermitRootLogin prohibit-password
Permissions | World-writable files in /opt | fixed | CRITICAL | WAS 2,007 source files o+w (incl. private.pem parent dir drwxrwxrwx) → fixed via chmod -R o-w; private.pem itself was already 0600
Permissions | .env.production mode | OK | info | 0600 root:root — correct
Permissions | Husky hooks | fixed | low | WAS drwxrwxrwx + 0o666 hook files → tightened to drwxr-xr-x + 0o644/0o755
PostgreSQL | Connection count | OK | info | 7 active
PostgreSQL | Database size | OK | info | 29 MB (gacp_db)
Redis | Memory usage | info | info | Could not query via redis-cli (NOAUTH) — backend reports healthy
Process | Top CPU process | info | info | gunicorn 14.8% (cadvisor 9.5%, dockerd 3.3%)
GACP | git HEAD | OK | info | deploy/production tip = ffa07d4 (Merge main v3.4.2)
GACP | git working tree | OK | info | clean
GHCR | Weekly cleanup workflow | fixed | low | ADDED — Sundays 03:23 UTC, keeps newest 30 sha-* + all v* + *-latest
Logs | Recent deploy logs | OK | info | 20260428-135046 / 140848 / 143644 in /var/log/gacp-deploys/
Logs | Secret rotation log | OK | info | 5 entries today (1 ROLLBACK + 4 ROTATED)
Documentation | docs/architecture/ | OK | info | 8 markdown + 1 HTML prototype + 3 office artifacts (this workbook + pptx + docx)

## Decisions Pending
# | Decision | Options | Recommendation
(a) | Tenant #2 onboarding within 4 weeks? | YES → flip order: do A6-3 (NOT NULL + RLS) before A5 NO → keep A5/A6 in parallel per timeline memo (recommended default) | NO — parallel A5/A6 unless tenant #2 actually within window
(b) | Accessibility statement source | (a) translate gov.uk model statement (~4 h Thai legal review) (b) wait for DTAM template (c) placeholder draft, replace later | (c) placeholder — ship when /accessibility route lands at W5, replace with (a) after legal review
(c) | RLS rollout window | (a) Sun 02:00-04:00 ICT (with daily backup window) (b) coordinated with tenant #2 onboarding (c) soft-rollout 1 week observe-only → flip to enforce | (c) → (a). Soft week catches every offending query; flip is a 30-second ALTER POLICY